## Runbook
DEPT® Runbook Template — Metadata
Fill in each value in column B. Do not rename this sheet. Then fill the 'Content' sheet with your phases, sections and tasks.
Slug | banking-architect-greenfield | Unique ID for this runbook. Use lowercase letters and hyphens only. E.g. banking-architect-greenfield
Title | Banking Architect — Greenfield Engagement | Full display title shown on the runbook page.
Role | architect | architect ¦ devops ¦ developer ¦ qa ¦ pm ¦ ba
Domain | banking | banking ¦ ecommerce ¦ manufacturing ¦ healthcare ¦ generic
Type | greenfield | greenfield ¦ brownfield
Description | 30-60-90 day engagement playbook for new banking builds on Adobe Experience Cloud. | One or two sentences shown below the title on the reader page.
Status | draft | draft (not visible to learners) ¦ published (visible on /runbook index)

## Content
type | title | description | owner | tools | timing | url | notes
phase ¦ section ¦ task ¦ step ¦ checklist ¦ link | Main text for this row | Supporting detail (optional) | Who does this? E.g. Architect, DevOps (task rows only) | Comma-separated. E.g. AEM, Adobe IO, Jira (task rows only) | When. E.g. Day 1, Week 2 (phase/section/task rows) | Full URL — used for link rows | Optional freeform notes (task rows only)
phase | Days 1–30: Onboarding | First month — environment, access, and discovery |  |  | Days 1–30
section | First Week | Immediate priorities before first client meeting |  |  | Day 1–5
task | Set up development environment | Clone repos, install SDKs, configure local AEM | Architect | AEM, Adobe IO, Git | Day 1 |  | Use the standard DEPT® dev-env script from the repo wiki
step | Clone the project repository |  |  |  |  | https://github.com/dept/your-repo
step | Run the local-setup script | Installs AEM 6.5 + dispatcher locally
checklist | VPN access confirmed
checklist | Adobe IO console access granted
link | DEPT® AEM starter kit |  |  |  |  | https://github.com/dept/aem-starter
task | Introduce yourself to the client team |  | Architect |  | Day 1
step | Send intro email with your working hours and primary contact
checklist | Client Slack / Teams channel joined
section | Weeks 2–4 | Discovery and architecture baseline |  |  | Day 6–30
task | Run CODE-CODER discovery workshop | Walk the client through all 14 nodes | Architect | Code-Coder Checklist | Week 2
step | Book a 3-hour working session with client architect + PO
step | Walk through the checklist PDF with client |  |  |  |  | https://internal.in.deptagency.com/anatomy/code-coder-checklist.html
checklist | All red/amber items have an owner and a date
phase | Days 31–60: Integration | Build the first working vertical |  |  | Days 31–60
section | Architecture decisions |  |  |  | Week 5–6
task | Document ADRs for top 5 decisions |  | Architect | Confluence, ADR template | Week 5 |  | One ADR per decision — see DEPT® ADR template
step | List candidate decisions in the project wiki
step | Run async review with engineering lead — 48 h comment window
checklist | ADRs reviewed and signed off by client architect
phase | Days 61–90: Stabilisation | Handover readiness and ongoing ops |  |  | Days 61–90
section | Knowledge transfer |  |  |  | Week 10–12
task | Record architecture walkthrough video |  | Architect | Loom, Confluence | Week 11
step | Record a 20-min Loom covering system topology, data flows, key ADRs
checklist | Video link added to project Confluence home

## Legend
Row type reference
type | what it does | tips
phase | Top-level block (e.g. Days 1–30). Sets timing for the block. | Required for each major phase. Appears as a large section header.
section | Sub-group within a phase (e.g. First Week, Architecture). | Optional — use when a phase has multiple distinct sub-areas.
task | Concrete thing to do. The main unit of the runbook. | Fill owner, tools, and timing here. Steps/checklist go below.
step | Numbered action inside a task (title = the step text). | url column can hold a link for this step. description adds context.
checklist | Checkbox item inside a task (title = the item text). | Keep items short. No url or owner needed.
link | Reference link inside a task (title = link label, url = href). | Use for docs, tools, templates. Appears as a clickable link.